## Sprint i
Contribution %
User Story | Story Tasks | ID | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Josh | Anthony | Evan | Mohammed
Establish user stories | Create initial list of stories | 0 | 1 | Establish documentation, initial code, and UI design | KA | 1 | 1 | 25 | 25 | 25 | 25
| Vote on which stories to keep | 1 | 1 |  | KA | 1 | 1 | 25 | 25 | 25 | 25
| Edit stories for final list | 2 | 1 |  | KA | 1 | 1 | 25 | 25 | 25 | 25
Establish functional and nonfunctional requirements | Produce list of desired project features | 3 | 1 |  | KA | 1 | 1 | 40 | 20 | 20 | 20
| Produce list of functional and nonfunctional requirements | 4 | 1 |  | KA | 1 | 1 | 40 | 20 | 20 | 20
| group requirements by associated features that they fulfill | 5 | 1 |  | KA | 1 | 1 | 40 | 20 | 20 | 20
| Fill out associated sections of the SRS | 6 | 1 |  | KA | 1 | 1 | 40 | 20 | 20 | 20
Prepare Zenhub Kanban | Complete Product Backlog | 7 | 1 |  | KA | 1 | 1 | 70 | 10 | 10 | 10
| Complete Sprint 1 Backlog | 8 | 1 |  | KA | 1 | 1 | 70 | 10 | 10 | 10
| Move necessary tasks into Kanban | 9 | 1 |  | KA | 1 | 1 | 70 | 10 | 10 | 10
Prepare initial code for opening a page | Choose language and environment for project | 10 | 1 |  | KA | 2 | 2 | 0 | 50 | 50 | 0
| Make a visual starter code to recreate the main UI | 11 | 1 |  | F | 4 | 4 | 0 | 50 | 50 | 0
| Test that the code works | 12 | 1 |  | NF | 2 | 2 | 10 | 40 | 40 | 10
Make mockups for UI navigation | Plan needed UIs | 13 | 1 |  | KA | 1 | 1 | 10 | 10 | 10 | 70
| Design visual mockups | 14 | 1 |  | KA | 4 | 4 | 0 | 0 | 0 | 100
| Make diagram of how the user moves through the UIs | 15 | 1 |  | KA | 2 | 2 | 10 | 10 | 10 | 70