## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | Establish user stories so that we can create backlogs and kanban | 1 | H | D | 2
2 | Establish functional and nonfunctional requirements so that we can complete the SRS | 1 | H | D | 2
3 | Prepare Zenhub Kanban so that we can organize our workflow | 1 | H | D | 1
4 | Prepare initial code for opening a page so that we have some source code to work off of | 1 | H | D | 4
5 | Make mockups for UI navigation so that we can discuss how the user will navigate the app | 1 | H | D | 4
6 | As a student, I want a well-designed UI so that I can navigate my way around it with ease. | 2 | H | IP | 8
7 | As a user, I want to use simple delimiters in my notes so that I have to take minimal extra time while writing in class | 2 | H | IP | 4
8 | As a student, I want to have an interface that is easy to traverse so that I enjoy studying more | 2 | H | IP | 8
9 | As a student, I want to be able to make and export flashcards without having to make an account so that I do not have to give anyone my information | 2 | H | IP | 4
10 | As a student, I want to be able to sort my flash cards into separate sets to organize my large course load. | 3 | H | W | 6
11 | As a student, I want to be able to interactively study with my flash cards to improve how well I retain information | 3 | H | W | 8
16 | As a student, I want the app to remind me when I'm due to study again so that I maintain a consistent studying schedule | 3 | M | W | 2
12 | As a student, I want a reviewing cards to be faster than with Ankidroid to make reviewing information less time consuming. | 4 | M | W | 3
13 | As an educator, I want there to be certain flashcard templates so that I can utilize them for different subjects. | 4 | M | W | 4
14 | As a user, I want to have access to my apps through a computer or my phone so that it’s at any time. | 4 | M | W | 10
15 | As a student, I want to be able to make notes on the flash cards I fail to remind me ways to remember (e.g. mnemonic devices) so I can more easily associate ideas | 4 | M | W | 4
17 | As a student, I want my key flashcards to be emailed to me before a test day so that I can check them | 5 | L | W | 2
18 | As a student, I want to color code and label my flashcards so that I can be more organized when studying | 5 | L | W | 4
19 | As a student, I want the app to automatically select for me the cards which I need to review the most to make studying efficient. | 5 | L | W | 4
20 | As a student, I want transparency in how the setting options change review scheduling so that I can tailor my studying for my own preferences. | 5 | L | W | 2