## Sprint i
Contribution %
Story ID | User Story | Task ID | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Josh | Anthony | Evan | Mohammed
1 | Establish user stories | 1 | Create initial list of stories | 1 | Establish documentation, initial code, and UI design | KA | 1 | 1 | 25 | 25 | 25 | 25
|  | 1.1 | Vote on which stories to keep | 1 |  | KA | 1 | 1 | 25 | 25 | 25 | 25
|  | 1.2 | Edit stories for final list | 1 |  | KA | 1 | 1 | 25 | 25 | 25 | 25
2 | Establish functional and nonfunctional requirements | 2 | Produce list of desired project features | 1 |  | KA | 1 | 1 | 40 | 20 | 20 | 20
|  | 2.1 | Produce list of functional and nonfunctional requirements | 1 |  | KA | 1 | 1 | 40 | 20 | 20 | 20
|  | 2.2 | group requirements by associated features that they fulfill | 1 |  | KA | 1 | 1 | 40 | 20 | 20 | 20
|  | 2.3 | Fill out associated sections of the SRS | 1 |  | KA | 1 | 1 | 40 | 20 | 20 | 20
3 | Prepare Zenhub Kanban | 3 | Complete Product Backlog | 1 |  | KA | 1 | 1 | 70 | 10 | 10 | 10
|  | 3.1 | Complete Sprint 1 Backlog | 1 |  | KA | 1 | 1 | 70 | 10 | 10 | 10
|  | 3.2 | Move necessary tasks into Kanban | 1 |  | KA | 1 | 1 | 70 | 10 | 10 | 10
4 | Prepare initial code for opening a page | 4 | Choose language and environment for project | 1 |  | KA | 2 | 2 | 0 | 50 | 50 | 0
|  | 4.1 | Make a visual starter code to recreate the main UI | 1 |  | F | 4 | 4 | 0 | 50 | 50 | 0
|  | 4.2 | Test that the code works | 1 |  | NF | 2 | 2 | 10 | 40 | 40 | 10
5 | Make mockups for UI navigation | 5 | Plan needed UIs | 1 |  | KA | 1 | 1 | 10 | 10 | 10 | 70
|  | 5.1 | Design visual mockups | 1 |  | KA | 4 | 4 | 0 | 0 | 0 | 100
|  | 5.2 | Make diagram of how the user moves through the UIs | 1 |  | KA | 2 | 2 | 10 | 10 | 10 | 70
6 | As a student, I want a well-designed UI so that I can navigate my way around it with ease. | 6 | Add import option to mockup | 2 | Progress the code for the UI and text processing | F | 1 | 1 | 0 | 0 | 0 | 100
|  | 6.1 | Add additional mockups for remaining app functions | 2 |  | KA | 2 | 1 | 0 | 0 | 0 | 100
|  | 6.2 | Implement one or two UI mockups as code | 2 |  | NF | 4 | 4 | 0 | 90 | 0 | 10
7 | As a user, I want to use simple delimiters in my notes so that I have to take minimal extra time while writing in class | 7 | Decide list of delimiters to allow | 2 |  | KA | 1 | 1 | 0 | 0 | 100 | 0
|  | 7.1 | Write code for processing text using those delimiters | 2 |  | F | 3 | 3 | 0 | 0 | 100 | 0
|  | 7.2 | Write code for outputting the resulting flashcards when processing text | 2 |  | F | 2 | 1 | 0 | 0 | 100 | 0
8 | As a student, I want to have an interface that is easy to traverse so that I enjoy studying more | 8 | Propose list of menu buttons | 2 |  | KA | 1 | 0 | 0 | 0 | 0 | 0
|  | 8.1 | Diagram how a user can navigate to/from each app function | 2 |  | KA | 1 | 0 | 0 | 0 | 0 | 0
|  | 8.2 | Remove any unecessary steps to make navigation quicker | 2 |  | NF | 1 | 0 | 0 | 0 | 0 | 0
9 | As a student, I want to be able to make and export flashcards without having to make an account so that I do not have to give anyone my information | 9 | Determine what benefits an account provide | 2 |  | KA | 1 | 0 | 0 | 0 | 0 | 0
|  | 9.1 | Propose alternative methods of getting this information or working without it | 2 |  | KA | 1 | 0 | 0 | 0 | 0 | 0
|  | 9.2 | Implement these decisions into the code and mockups | 2 |  | NF | 3 | 0 | 0 | 0 | 0 | 0